## Sheet 1
Table 1
Task | Description | Start | End
Backend Development
Setup NestJS Project | Initialize NestJS project structure | 2023-08-20 | 2023-08-20
Create Entities | Define data entities for User, Partner, Services, LogService. | 2023-08-20 | 2023-08-20
| Implement data access for entities | 2023-08-20 | 2023-08-20
Implement Controllers | Develop API controllers for different endpoints | 2023-08-21 | 2023-08-22
Implement the authentication | Add Bearer token with private public keys to secret key | 2023-08-21 | 2023-08-21
| Add AuthGuard controllers | 2023-08-21 | 2023-08-22
Frontend Development
Setup ReactJS Project | Initialize ReactJS project structure | 2023-08-23 | 2023-08-23
Create Login Screen | Develop login screen UI | 2023-08-23 | 2023-08-23
Fetch Data from backend | Get data from service, and display | 2023-08-23 | 2023-08-23
Create Services Screen | Design services screen UI | 2023-08-23 | 2023-08-23
| Implement Subscribe functionality | 2023-08-23 | 2023-08-23
| Implement Subscribe functionality | 2023-08-23 | 2023-08-23
UI improvement
Database Setup
Setup MongoDB Database | Set up and configure MongoDB
Testing
Create Frontend test |  | 2023-08-24 | 2023-08-24